## CSP Annual Plan 2024-25
Project | Project status | Link to final report | Planned cost per annum
Interaction projects
INT2022-02 Identification of seabirds captured in New Zealand fisheries (1 July 2024 to 30 June 2025) | In progress; Year 3 of 3 due for completion November 2026 | To be provided on completion | 80000
INT2022-03 Identification, storage and genetics of cold-water coral bycatch specimens (1 July 2024 to 30 June 2025) | In progress; Year 3 of 3 due for completion May 2026 | To be provided on completion | 80000
INT2022-05 Determining the resilience of the black coral Antipathella fiordensis to fisheries impacts | Delayed; Year 3 of 3 due for completion September 2026 | To be provided on completion | 30000
INT2023-04 Identification of marine mammals, turtles and protected fish captured in New Zealand fisheries (1 July 2024 to 30 June 2025) | In progress; Year 2 of 3 due for completion April 2026 | To be provided on completion | 15000
INT2023-06 Investigating the impact of fisheries on endangered hoiho diet, microbiome, and disease susceptibility | In progress; Year 2 of 2 due for completion May 2026 | To be provided on completion | 50000
INT2024-01 Observing commercial fisheries | Delayed; observed protected species interaction data analysis will be provided approximately June 2026 | To be provided on completion | 1111685
INT2024-02 Port-based audit and Protected Species retention programme | Completed | Port-Based Data Collection and Specimen Retention Programme: csp report | 100000
INT2024-03 Characterising turtle and seabird bycatch risk factors over the surface longline soak period | Delayed, year 2 of 2 in progress | To be provided on completion | 20000
INT2024-04 Exploring impacts and recovery potential of protected deep-sea stony corals, utilising Remotely Operated Vehicle capability on RV Sonne in the New Zealand region | Year 1 of 2 completed | Exploring impacts and recovery potential of protected deep-sea stony corals: csp report | 140000
INT2024-05 Testing bycatch mitigation scenarios for protected corals in New Zealand using best available information | Delayed., due for completion in 2026/27. | To be provided on completion | 80000
INT2024-06 Interaction of spotted shags with northern North Island set net fisheries | Completed | Interaction of spotted shags with northern North Island set net fisheries: csp report | 30000
INT2024-07 Collection and curation of tissue samples from protected fishes and turtles | Year 1 of 3 completed. | Collection and curation of tissue samples from protected fishes and turtles: csp report | 20000
INT2024-08 Westland petrel overlap with commercial fishing effort | Completed | Westland petrel overlap with domestic fishing effort: CSP report | 20000
Population projects
POP2022-01 Black Petrel population monitoring | Completed | Black petrel population monitoring 2024/2025: csp report | 100000
POP2022-08 Auckland Island seabird research: Gibson’s and white-capped albatross | Completed | Auckland Islands seabird research 2024/25: csp report | 160000
POP2022-10 Antipodean island seabird research: Antipodean albatross + white chinned petrel | Completed | Antipodes Island seabird research 2024/25: csp report | 160000
POP2023-01 Aerial survey of leatherback turtles off Northeast North Island | Completed | Aerial survey of leatherback turtles in the waters off North Island, New Zealand: csp reports | 100000
POP2023-02 Southern Buller's population study | Year 2 of 3 completed | Population studies of Southern Buller’s albatrosses at Tini Heke / The Snares Islands: csp report | 150000
POP2023-03 Updated population estimate and marine habitat utilisation of yellow-eyed penguins/hoiho breeding on Campbell Island | Project completed, awaiting final report for publication to website | To be provided on completion | 90000
POP2023-04 Campbell Island seabird research | Completed | Campbell Island seabird research 2024/25: csp report | 90000
POP2023-05 Auckland Islands New Zealand sea lions | Year 2 of 3 completed | NZ sea lion monitoring at the Auckland Islands 2024/25: csp report | 150000
POP2024-01 Flesh-footed Shearwater population monitoring | Completed | Flesh-footed shearwater population monitoring and estimate 2024/25: csp report | 30000
POP2024-02 Improving knowledge on coral life history traits: assessing reproductive capacity to infer productivity, vulnerability and resilience of protected deep sea corals in the New Zealand region | Year 1 of 2 completed | Improving knowledge on coral life history traits: csp report | 65000
Mitigation projects
MIT2023-06 Underwater line setting devices for bottom longline vessels | Delayed due to operational factors, due for completion June 2026 | To be provided on completion | 75000
MIT2024-01 Protected Species Liaison Programme | Year 2 of 3 in progress | To be provided on completion | 250000
MIT2024-02 Enhancing seabird bycatch mitigation across the set and soak periods in surface longline fisheries | Completed | Understanding and mitigating seabird and turtle bycatch during the pelagic longline soak period: csp report | 140000
MIT2024-03 Assessment of weighted hooks as a seabird bycatch mitigation option for surface longline fisheries | Completed | Assessment of weighted hooks as a seabird bycatch mitigation option for surface longline fisheries: csp reports | 40000
MIT2024-04 Sink rate management tool for small vessel bottom longline | Completed | Sink rate management tool for small vessel bottom longline: csp report | 30000
MIT2024-05 Testing the utility of visual deterrent options to mitigate incidental bycatch of protected species in set nets | Completed | Testing the utility of visual deterrent options to mitigate incidental bycatch of protected species in set nets: csp reports | 80000
MIT2024-06 Efficacy of seabird mitigation in large vessel trawl | Year 2 of 2 in progress, due for completion June 2027 | To be provided on completion | 50000
MIT2024-07 Hector's dolphin acoustic deterrence devices in trawl and set net fisheries | Year 2 of 2 in progress, due for completion June 2026 | To be provided on completion | 60000